## Direct Seed
actual seed date | week number | seed date | Crop | Variety | Color | Succession number | Field Location | Seed Plate | rows per bed | actual rows/bed | actual bed feet | BED FEET | seed quantity | notes
MAKE ALL QUANTITY & TIMING NOTES ON THIS SHEET; will need to enter into this sheet + map at end
|  | 2019-03-15 | Sugar Snap Pea |  |  |  | house garden
|  | 2019-03-15 | Bupleurum Garibaldi |  |  |  | EFF | radish | 3 |  |  | 100
|  | 2019-03-15 | Dill Dukat |  |  | 1 | EFF | radish | 3 |  |  | 100
|  | 2019-03-15 | Nigella | Black Pod (Johnnys) |  |  | EFF | lettuce | 3 |  |  | 50
|  | 2020-03-15 | Bells of Ireland |  |  |  | EFF |  | 3 |  |  | 50
| 16 | 2016-04-15 | Dahlias | tubers |  |  | EFF
| 16 | 2014-04-15 | Ammi visnaga | Green Mist |  | 1 | EFF | lettuce | 3 |  |  | 100
| 16 | 2016-04-15 | Dill | Dukat |  | 2 | EFF | radish | 3 |  |  | 100
|  |  | onion starts |  |  |  | EFF
| 18 | 2016-05-01 | Dill | Dukat |  | 3 | EFF | radish | 3 |  |  | 100
| 18 | 2020-05-01 | Artemesia annua | Sweet Annie |  |  | BF rear
| 20 | 2018-05-15 | Zinnia | Benary's | Mix |  | upper |  | 3 |  |  | 100
| 20 | 2018-05-15 | Zinnia | Magna | Mix |  | upper |  | 3 |  |  | 100
| 23 | 2018-06-01 | Bean | Rolande
| 23 | 2014-06-01 | Celosia | Plume | asst | 1 | PLASTIC | BF8,10, WB |  |  | 440 | 300
| 25 | 2018-06-10 | Zinnia | Benary's | Mix |  | upper |  | 3 |  | 175 | 100
| 25 | 2018-06-10 | Zinnia | Magna |  |  | upper |  | 3 |  | 0 | 50
| 25 | 2019-06-10 | Amaranthus | Green Cascade |  |  | upper | hand seed |  |  |  |  | 20M
| 25 | 2019-06-10 | Amaranthus | Velvet Curtains |  |  | upper | hand seed |  |  |  |  | 10M
| 28 | 2019-06-10 | Amaranthus | Coral Fountain |  |  | upper | hand seed |  |  |  |  | 10M
| 25 | 2015-06-20 | Celosia | Plume | asst | 2 | PLASTIC | BF4 |  |  | 450 | 250
| 25 | 2014-06-20 | Setaria italica | Macrochaeta |  |  | upper | radish | 2 |  | 100 | 65 | 15M
| 25 | 2018-06-20 | Millet | Limelight |  |  | upper |  | 2 |  | 100 | 65 | 8M
| 25 | 2014-06-20 | Sorghum | Colored uprights | Mix |  | upper | beet | 4 |  | 0 | 130 | 40M
| 25 | 2020-06-20 | Sorghum | Hegari |  |  | upper | beet | 10rows |  |  | 130 | 40M
|  |  | sorghum cover crop |  |  |  | rest of upper rear
| 27 | 2018-07-01 | Zinnia | Benary's | Mix |  | upper | plastic | 2 |  |  | 150
| 27 | 2018-07-01 | Amaranthus | Coral Fountain |  |  | EFF | hand seed |  |  | 50 |  | 10M
| 27 | 2018-07-01 | Amaranthus | Red Cascade |  |  | EFF | hand seed |  |  | 50 |  | 20M
| 27 | 2018-07-01 | Amaranthus | Velvet Curtains |  |  | EFF | hand seed |  |  | 50 |  | 20M
| 27 | 2019-07-01 | Ammi visnaga |  |  |  | BF rear |  | 3 |  | 50
| 27 | 2019-07-01 | Orlaya |  |  |  | BF rear |  | 3 |  | 50
| 27 | 2014-07-01 | Celosia | Plume | asst | 3 | EFF |  | 3 |  | 230 | 250
did magenta, yellow
|  | 2020-07-01 | Celosia | saved Cramers Burgundy
| 30 | 2015-07-20 | Celosia | Plume | asst | 4 | EFF |  | 3 |  | 200 | 300
did peach, burg cc
| 31 | 2016-08-01 | Celosia | Plume | asst | 5 | EFF |  | 3 |  | SKIP | 100
| 38 | 2014-09-15 | Bupleurum | Garibaldi |  |  | BFRear | radish | 3 |  | 350 | 200
| 41 | 2019-10-01 | Poppy | French Flounce |  |  |  | hand seed
| 41 | 2019-10-01 | Poppy | Lauren's Dark Grape |  |  |  | hand seed
| 41 | 2019-10-01 | Poppy | saved |  | Upper |  | hand seed |  |  | 100
| 41 | 2019-10-01 | Nigella | Green Marbles |  | upper |  | radish | 3 |  | 100 | 100
| 41 | 2019-10-01 | Nigella | Black Marbles |  | upper |  | radish | 3 |  | 100 | 100
| 41 | 2014-10-01 | Larkspur | QIS | Lilac | upper |  | radish | 3 |  | 80 | 50 | 5M
| 41 | 2014-10-01 | Larkspur | QIS | Dark Blue | upper |  | radish | 3 |  | 90 | 100 | 10M
| 41 | 2014-10-01 | Wheat | Silver Tip |  |  |  | beet | 3 |  | 100 | 50
| 41 | 2014-10-01 | Spinach, lettuce
| 41 | 2014-10-01 | Garlic
total/planting
|  | 2014-04-01 | Sunflower | Procut | Orange DMR | 1 | U24 |  | 3 |  | 0 | 100 |  | 100
|  | 2014-04-10 | Sunflower | Procut | Orange DMR | 2 | U24 |  | 3 |  | 265 | 200 |  | 200
|  | 2014-04-20 | Sunflower | Vincent's Choice DMR |  | 3 | U23 |  | 3 |  | 275 | 300 |  | 300
|  | 2014-04-30 | Sunflower | Premier | Orange | 4 | U22 |  | 3 |  | 300 | 300 |  | 300
|  | 2015-05-10 | Sunflower | Procut | Orange DMR | 5 | U21-20 |  | 3 |  | 600 | 600 |  | 600
|  | 2014-05-20 | Sunflower | Premier | Orange | 6 | U17-19, 16 is short |  | 3 |  | 1100 | 1200 |  | 1200
|  | 2014-05-30 | Sunflower | Procut | Orange DMR | 7 | U9-15 short |  | 3 |  | 1320 | 1200 |  | 1200
|  | 2015-06-09 | Sunflower | Premier | Orange | 8 | U6-8 short, U8.1 long, 8.2 & 8.3 short start at trunk end (triangle of open space btwn suns & gomph) |  | 3 |  | 800 | 1200 | 1300 | 1200
|  |  |  | vincents choice | [6 empty] | 500
|  | 2019-06-19 | Sunflower | Procut | Orange DMR | 9 | new 1-8 |  | 3 |  | 1280 | 1200 |  | 1200
|  | 2014-06-29 | Sunflower | Vincent's Choice DMR |  | 10 | new 12-15 |  | 3 |  | 675 | 900 |  | 1200
|  | 2020-06-29 | Sunflower | Procut | White Nite | 10 | new 9-11 |  | 3 |  | 550 | 300 |  |  | use up seed & then plant rest procut
|  | 2014-07-09 | Sunflower | Vincent's Choice DMR |  | 11 | new 16-20, short 21-23 |  | 3 |  | 1050 | 1200 |  | 1200
|  | 2014-07-19 | Sunflower | Procut | Orange DMR | 12 | U1-3 |  | 3 |  | 850 | 1200 |  | 1200
|  | 2014-07-29 | Sunflower | Procut | Orange DMR | 13 | U4C-7 |  | 3 |  | 1100 | 1000 |  | 1000
|  | 2020-07-29 | Sunflower | Ziggy |  | 13 | U4A |  |  |  | 50
|  | 2020-07-29 | Sunflower | Marley |  | 13 | U4B |  |  |  | 50
|  | 2014-08-08 | Sunflower | Procut | Orange DMR | 14 | U8-10 short |  | 3 |  | 600 | 400 |  | 400
|  | 2014-08-18 | Sunflower | Procut | Orange DMR | 15 | U11 |  | 3 |  | combine | 200 |  | 200
|  | 2017-08-29 | Sunflower | Procut | Orange DMR | 16 |  |  | 3 |  |  | 75 |  | 75

## Transplants
Seed Trail? | Seeding date | seeding week | Actual Seeding Date | Seeder Initials | Crop | Variety | Color | PLANTS NEEDED | where to be planted | Actual number of flats | number of flats | flat size | Planting Notes | total flats 2019 | total flats 2020
| 2020-03-15 |  | 2020-03-17 |  | Brassica | Crane FEATHER | King | 432 |  | 6 | 6 | 72
| 2020-04-10 | 15 | 2020-04-13 |  | Celosia plume | saved | Magenta | 432 |  | 6 | 6 | 72 | seed heavily (seed all saved plume seed heavily)
***this is the succession to really watch for damping off!
| 2016-04-20 | 17 | 2020-04-20 |  | Basil | Sweet Dani |  | 1728 | split 4/27 | 24 | 24 | 72
| 2016-04-20 | 17 | 2020-04-20 |  | Celosia c.c. | Chief | Fire | 2592 |  | 36 | 36 | 72 | ***this is the succession to really watch for damping off!
| 2016-04-20 | 17 | 2020-04-20 |  | Celosia c.c. | Chief | Persimmon | 2592 |  | 36 | 36 | 72
| 2016-04-20 | 17 | 2020-04-20 |  | Celosia plume | Forest Fire |  | 864 |  | 12 | 12 | 72
| 2016-04-20 | 17 | 2020-04-20 |  | Celosia plume | saved | yellow | 576 |  | 8 | 8 | 72
| 2019-04-20 | 17 | 2020-04-20 |  | Celosia plume | Sunday saved | Pink Bright | 720 |  | 10 | 10 | 72
| 2019-04-20 | 17 | 2020-04-20 |  | Celosia plume | Sunday saved | Orange | 576 |  | 8 | 8 | 72
| 2016-04-20 | 17 | 2020-04-20 |  | Gomphrena | QIS | Lilac | 1440 |  | 20 | 20 | 72
| 2016-04-20 | 17 | 2020-04-20 |  | Gomphrena | QIS | Purple | 3600 |  | 50 | 50 | 72 | seed some from both sources & keep track
| 2016-04-20 | 17 | 2020-04-20 |  | Gomphrena | QIS | White | 144 |  | 2 | 2 | 72
| 2017-04-20 | 17 | 2020-04-20 |  | Marigold | Jedi | Orange | 576 |  | 8 | 8 | 72
| 2020-04-20 | 17 | 2020-04-20 |  | Marigold | Coco | Deep Orange | 576 |  | 7 | 8 | 72
T | 2020-04-20 | 17 | 2020-04-20 |  | Marigold | Chedi | Orange | 72 |  | 1 | 1 | 72 | be sure to note difference of jedi vs chedi
T | 2020-04-20 | 17 | 2020-04-20 |  | Marigold | Mayan | Orange | 72 |  | 1 | 1 | 72
| 2016-04-20 | 17 | 2020-04-20 |  | Scabiosa stellata |  |  | 288 |  | 4 | 4 | 72
| 2019-04-20 | 17 | 2020-04-20 |  | Scabiosa | Cut Brite |  | 288 |  | 4 | 4 | 72
RT | 2017-04-20 | 17 | 2020-04-20 |  | Zinnia | Magna | Mix | 288 |  | 4 | 4 | 72 | Please make note to label these in the field
| 2019-04-20 | 17 | 2020-04-20 |  | Zinnia | Benary's Giant Mix |  | 288 |  | 4 | 4 | 72
T | 2019-04-20 | 17 | 2020-04-20 |  | Zinnia | EXP | Orange | 144 |  | 2 | 2 | 72
T | 2019-04-20 | 17 | 2020-04-20 |  | Zinnia | EXP | Purple | 144 |  | 2 | 2 | 72
add | 2020-04-20 |  | 2020-04-20 |  | Gomphrena | Audray | Purple Red |  |  | 7 |  | 72
[11 empty] | 244 | total flats this planting
| 2017-05-05 | 20 | 2020-04-30 |  | Ageratum | Blue Sensation |  | 864 |  | 12 | 12 | 72 | seed thickly? Unsure how saved will germinate.
| 2017-05-05 | 20 | 2020-05-01 |  | Aster | Matsumoto | Blue | 1728 |  | 24 | 24 | 72 | compare with Fujimi Purple
| 2017-05-05 | 20 | 2020-05-01 |  | Aster | Fujimi | Purple |  |  | 10 | 10 | 72 | Please make a note to label these in the field.
| 2017-05-05 | 20 | 2020-05-01 |  | Aster | Matsumoto | White | 288 |  | 4 | 4 | 72
| 2017-05-05 | 20 | 2020-05-01 |  | Aster | Matsumoto | Light Blue | 720 |  | 10 | 10 | 72
| 2019-05-05 | 20 | 2020-05-01 |  | Aster | Matsumoto | Apricot | 288 |  | 4 | 4 | 72
| 2016-05-05 | 20 | 2020-05-05 |  | Celosia c.c. | Chief | Fire | 2880 |  | 40 | 40 | 72
| 2017-05-05 | 20 | 2020-05-05 |  | Celosia c.c. | Kurume | Orange Red | 1440 |  | 20 | 20 | 72
[11 empty] | 124 | total flats this planting
add |  |  | 2020-05-11 |  | Marigold | Jedi | Orange |  | 128 | 6
| 2019-05-15 | 21 | 2020-05-14 |  | Aster | Matsumoto | Blue | 2880 | 128 | 23 | 40 | 72
| 2019-05-15 | 21 | 2020-05-14 |  | Aster | Matsumoto | Apricot | 288 | 128 | 3 | 4 | 72
| 2016-05-15 | 20 | 2020-05-14 |  | Celosia plume | Saved | magenta | 1296 |  | 24 | 18 | 72
| 2016-05-15 | 20 | 2020-05-14 |  | Celosia plume | Saved | peach | 432 |  | 6 | 6 | 72
| 2016-05-15 | 20 | 2020-05-14 |  | Celosia plume | Saved | orange | 432 |  | 6 | 6 | 72
T | 2016-05-15 | 21 | 2020-05-14 |  | Celosia plume | Cristi | Purple | 144 |  | 2 | 2 | 72
T | 2016-05-15 | 21 | 2020-05-14 |  | Celosia plume | Red Ace |  | 144 |  | 2 | 2 | 72
T | 2016-05-15 | 21 | 2020-05-14 |  | Celosia plume | Act Rima | Rose | 144 |  | 2 | 2 | 72
| 2016-05-15 | 21 | 2020-05-12 |  | Gomphrena | QIS | Purple | 2880 |  | 40 | 40 | 72
| 2017-05-15 | 21 | 2020-05-12 |  | Gomphrena | QIS | White | 432 |  | 10 | 6 | 72
| 2018-05-15 | 21 | 2020-05-12 |  | Gomphrena | QIS | Lilac | 2160 |  | 40 | 30 | 72
[11 empty] | 156 | total flats this planting
add |  |  | 2020-05-20 |  | Ageratum | Saved Blue Sensation |  |  | 10rows-9
| 2017-06-01 | 23 | 2020-06-01 |  | Aster | Matsumoto | Light Blue | 2880 | 128 | 28 | 40 | 72
| 2019-06-01 | 23 | 2020-06-01 |  | Aster | Matsumoto | White | 288 | 128 | 3 | 4 | 72
| 2019-06-01 | 23 | 2020-06-01 |  | Aster | King Size | Apricot | 432 | 128 | 4 | 6 | 72
| 2019-06-01 | 23 | 2020-06-01 |  | Aster | Lady Coral | Lavender |  | 128 | 3 | 4 | 72
| 2017-06-01 | 23 | 2020-06-02 |  | Marigold | Oriental | Deep Gold | 432 |  | 6 | 6 | 72
| 2017-06-01 | 23 | 2020-06-02 |  | Marigold | Coco | Deep Orange | 432 |  | 8 | 6 | 72
T | 2017-06-01 | 23 | 2020-06-02 |  | Marigold | Nosento | Lime Green | 72 |  | 1 | 1 | 72
T | 2017-06-01 | 23 | 2020-06-02 |  | Marigold | Royal Ball | Gold | 72 |  | 1 | 1 | 72
T | 2017-06-01 | 23 | 2020-06-02 |  | Marigold | Hermant | Deep Gold | 72 |  | 1 | 1 | 72
| 2017-06-01 | 23 | 2020-06-02 |  | Marigold | CRAZY SAVED |  | 288 |  | 4 | 4 | 72
| 2020-06-01 | 23 | 2020-06-02 |  | Rudbeckia | Sahara |  | 288 |  | 4 | 4 | 72
[11 empty] | 77 | total flats this planting
| 2018-06-15 | 24 | 2020-06-15 |  | Aster | Matsumoto | Blue | 1440 | 128 | 23 | 20 | 72
| 2018-06-15 | 24 | 2020-06-16 |  | Aster | Matsumoto | White | 288 | 128 | 2 | 4 | 72
| 2018-06-15 | 24 | 2020-06-16 |  | Aster | Matsumoto | Light Blue | 1440 | 128 | 23 | 20 | 72
| 2016-06-15 | 24 | 2020-06-16 |  | Celosia plume | Forest Fire |  | 1440 |  | 20 | 20 | 72
| 2016-06-15 | 24 | 2020-06-16 |  | Celosia plume | Saved | orange | 864 |  | 12 | 12 | 72
| 2019-06-15 | 24 | 2020-06-16 |  | Zinnia | Queen | Lime Red | 288 |  | 4 | 4 | 72
| 2019-06-15 | 24 | 2020-06-16 |  | Zinnia | Queen | Lime Orange | 288 |  | 4 | 4 | 72
[11 empty] | 84 | total flats this planting
| 2017-06-20 | 25 | 2020-06-19 |  | Marigold | Oriental | Deep Gold | 576 |  | 10 | 8 | 72 | see Michelle: may increase to 10
| 2017-06-20 | 25 | 2020-06-19 |  | Marigold | Jedi | Orange | 576 |  | 10 | 8 | 72
T | 2017-06-20 | 23 | 2020-06-19 |  | Marigold | Bengal | Orange | 72 |  | 1 | 1 | 72
T | 2017-06-20 | 23 | 2020-06-19 |  | Marigold | Janthra |  | 72 |  | 1 | 1 | 72
T | 2017-06-20 | 23 | 2020-06-19 |  | Marigold | Xochi | Orange | 72 |  | 1 | 1 | 72
| 2019-06-20 | 25 | 2020-06-19 |  | Snapdragon | Monaco | White | 576 |  | gh | 8 | 72
| 2019-06-20 | 25 | 2020-06-19 |  | Snapdragon | Monaco | Red | 216 |  | gh | 3 | 72
|  |  | 2020-06-22 |  | Aster | Matsumoto | Light Blue |  |  | 128 | 10
|  |  | 2020-06-22 |  | Aster | Matsumoto | Blue |  |  | 128 | 10
[11 empty] | 50 | total flats this planting
| 2018-07-01 | 27 | 2020-07-01 |  | Dusty Miller | New Look |  | 72 |  | gh | 1 | 72
| 2019-07-01 | 27 | 2020-07-01 |  | Stock | Japan All Double White Surf |  | 432 | 7 | gh | 6 | 72
| 2020-07-01 | 27 | 2020-07-01 |  | Stock | Milla Salmon |  | 432 | 5 | gh | 6 | 72
[11 empty] | 13 | total flats this planting
| 2020-07-10 | 28 | 2020-07-10 |  | Brassica | Flare | Rose |  | 0.5 | field | 1 | 72 | use up seed
| 2020-07-10 | 28 | 2020-07-10 |  | Brassica | Dream |  | 432 | 10 | field | 6 | 72 | want a total of 35-36 flats this planting -see Michelle for adjustment (all feather types)
T | 2020-07-10 | 28 | 2020-07-10 |  | Brassica | Crane RUFFLE | Bicolor | 288 | 3.5 | field | 4 | 72
| 2020-07-10 | 28 | 2020-07-10 |  | Brassica | Crane FEATHER | Queen | 1296 | 13 | field | 18 | 72
| 2020-07-10 | 28 | 2020-07-10 |  | Brassica | Lady First Lady |  | 432 | 5 | field | 6 | 72
| 2020-07-10 | 28 | 2020-07-10 |  | Stock | Japan All Double Yellow | Yellow (venus) | 432 | 6 | gh | 6 | 72
| 2020-07-10 | 28 | 2020-07-10 |  | Stock | Japan All Double White Surf |  | 576 | 8 | gh | 8 | 72
| 2020-07-10 | 28 | 2020-07-10 |  | Stock | Katz | Lavender Blue | 288 | 4 | gh | 4 | 72
| 2020-07-10 | 28 | 2020-07-10 |  | Stock | Vintage Brown |  | 288 | 4 | gh | 4 | 72
|  |  | 2020-07-10 |  | Strawflower | King Size Mix |  | 144 |  |  | 2 | 72
|  |  | 2020-07-10 |  | Strawflower | Monstrum White |  | 864 |  |  | 12 | 72
|  |  | 2020-07-10 |  | Strawflower | Fireball |  | 432 |  |  | 6 | 72
[11 empty] | 77 | total flats this planting
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Moonlight |  | 216 | 3 | gh | 3 | 72 | want 18 total trays kale/cabbage combined this seeding; ok to sub
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Lady White Lady |  | 216 | 3.5 | gh | 3 | 72
T | 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Lucir | Rose | 72 | 0.5 | gh | 1 | 72 | Use up seed
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Condor | White | 216 | 2 | gh | 3 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Condor | Red | 216 | 3 | gh | 3 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Crane | Pink | 144 | 2 | gh | 2 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Crane | White | 144 | 3 | gh | 2 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Brassica | Crane | Mix | 72 | 1.25 | gh | 1 | 72 | **plant all this seed (old); decrease others as needed
| 2020-07-20 | 30 | 2020-07-21 |  | Snapdragon | Chantilly | Light Salmon | 144 | 2 | gh | 2 | 72
| 2020-07-20 | 30 | 2020-07-21 |  | Snapdragon | Chantilly | Purple | 432 | 3 | gh | 6 | 72
|  |  | 2020-07-21 |  | Snapdragon | Calima | Deep Rose |  | 3 |  |  | 72
| 2020-07-20 | 30 | 2020-07-21 |  | Snapdragon | Cool | Crimson | 216 | 3 | gh | 3 | 72
| 2020-07-20 | 30 | 2020-07-21 |  | Snapdragon | Maryland | White | 216 | 3 | gh | 3 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Dianthus | Electron | Mix | 1440 | 20 |  | 20 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Dianthus | Bouquet | Purple | 1440 | 8.5 |  | 20 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Dianthus | Lace Mantle |  | 432 | 10 |  | 6 | 72 | use all seed
| 2020-07-20 | 30 | 2020-07-22 |  | Dianthus | Bodelstoz | Burgundy | 720 | 13 |  | 10 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Digitalis ferruginea | Gigantea |  | 144 | 2 |  | 2 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Digitalis purpurea | Alba |  | 144 | 2 |  | 2 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Digitalis purpurea | Suttons Apricot |  | 144 | 2 |  | 2 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Chrysanthemum parthenium | Balls Ultra Double |  | 576 | 8 |  | 8 | 72
| 2020-07-20 | 30 | 2020-07-22 |  | Chrysanthemum parthenium | White Wonder |  | 576 | 8 |  | 8 | 72
|  |  | 2020-07-22 |  | Dusty Miller | New Look
[11 empty] | 110 | total flats this planting
| 2020-07-25 | 31 | 2020-07-24 |  | Stock | Japan All Double | Yellow (venus) | 360 |  | 5 | 5 | 72
| 2020-07-25 | 31 | 2020-07-24 |  | Stock | Japan All Double White Surf |  | 360 |  | 5 | 5 | 72
[11 empty] | 10 | total flats this planting
|  |  | 2020-08-18 |  | Snapdragon | Chantilly | Purple |  |  | 2.5 |  | 72
|  |  | 2020-08-18 |  | Snapdragon | Chantilly | Light Salmon |  |  | 2.5 |  | 72

## Hillside Perennial Field
Field/Row (from North to South) | Order (from WEST to EAST - DIRT ROAD TO HOUSE) | Crop | Variety | Color | Length (feet) | Width (inches) | Actual Date In | Date Out | Number of plants | How started | Source | Notes
| Open space for spring 2020 |  |  |  | TRIAL |  | remove 2020
HP1 | A | Hydrangea | Annabelle |  |  |  | 2016-03-26 |  | 16 |  | dug from Jane Dunn's home
HP1 | B | Hydrangea | Annabelle |  |  |  | 2014-11-16 |  | 40 |  | moved from old farm | 3R, 5' spacing
HP1 | C | Hydrangea paniculata | Pinky Winky |  |  |  | 2015-10-31 |  | 10 |  | Maple Lane | 3R, 5' spacing
HP1 | D | Hydrangea paniculata | Pink Diamond |  |  |  | 2015-10-31 |  | 4 |  | Maple Lane | 3R, 5' spacing
HP1 | E | Hydrangea paniculata | Limelight |  |  |  | 2015-10-31 |  | 5 |  | Maple Lane | 3R, 5' spacing
HP1 | F | Hydrangea paniculata | Little Lime |  |  |  | 2015-10-31 |  | 2 |  | Diller | 3R, 5' spacing
HP1 | G | Hydrangea | Quick Fire |  |  |  | 2016-05-02 |  | 16 |  | Spring Meadow | 4R, 5' spacing
HP1 | H | Hydrangea | Quick Fire |  |  |  | 2019-10-20 |  | 16 |  | Maple Lane |  |  | extend bed to treeline 10/15/19
HP1 | among | Ornigthogalum |  |  |  |  | 1905-07-07 |  |  |  | Pete Roteveel
HP1 | among | Hyacinthoides |  |  |  |  | 2015, 2016 |  |  |  | Pete Roteveel
HP1 | among | Narcissus | Salome |  |  |  | 2017-11-15 |  | 50 |  | Pete Roteveel
HP1 | among | Narcissus | Sauda |  |  |  | 2017-11-15 |  | 50 |  | Pete Roteveel
HP1 | among | Narcissus | Pink Charm |  |  |  | 2018-11-10 |  | 50 |  | Pete Roteveel
HP1 | among | Narcissus | Marieke |  |  |  | 2018-11-10 |  | 50 |  | Pete Roteveel
HP1 | among | Narcissus | Dutch Master |  |  |  | 2019-11-15 |  | 50 |  | Pete Roteveel
HP1 | among | Hyacinthoides |  | White |  |  | 2019-11-15 |  | 100 |  | Pete Roteveel
HP2 | A | Hellebore | Brandywine |  |  | 48" | 2014-11-20 |  | 18 | plugs | North Creek Nusery | 2/2 pattern
HP2 | B | Hellebore |  | white |  | 48" | 2014-11-20 |  | 7 | trans from old farm | Giant | 2/2 pattern
HP2 | C | Hellebore (random) |  |  |  | 48" | 2014-11-20 |  | 1 | trans from old farm |  | 2/2 pattern
HP2 | C | Hellebore | Honey Hill Joy |  |  |  | 2020-04-09 |  | 3 |  | Newville Produce
HP2 | D | Hellebore | foetidus |  |  |  | 2017-03-30 |  | 14 | craigslist!
HP2 | E | Lysimachia clethroides |  |  |  |  | 2020-07-31 |  | 3-32 |  | Ball GET plants?
HP2 | E | Baptisia | Purple Smoke |  |  |  | 2019-10-15 |  | 2-50 |  | North Creek |  | none made it spring 2020
| F |  | solomons seal
HP2 | E | Astilbe | Purple Candles |  |  |  | 2020-05-19 |  | 25 plants |  | Walters Gardens
HP2 | F | Astilbe | Maggie Daley |  |  |  | 2020-05-15 |  | 25 plants |  | Walters Gardens
HP2 | G | Anemone | Honorine Jobert |  |  |  | 2020-06-02 |  | 1-50 |  | North Creek
HP2 | G | Anemone | Whirlwind | White |  |  | 2018-10-10 |  | 1-50 |  | GreenLeaf
HP2 | G | Convallaria | Bordeaux |  |  | 48" | 2016-04-25 |  | 200 | bare root | Walters Gardens |  | pips, small & a bit dry; hope will live
HP2 | G | Heucherella | Art Neuvo |  |  | 48" | 2016-04-29 |  | 14 | elle pot | ASCFG TRIAL | 4/4 pattern
HP2 | G | Astrantia
HP2 | H | Anemone | White |  |  | 48" | 2017-10-31 |  | 7 |  | Morgan Plant
HP2 | I | Anemone | Honorarie Jobert |  |  | 48" | 2017-05-16 |  | 25 plants |  | North Creek Nusery |  | fill in around lily of valley
HP2 | J | Dicentra spectabilis | Alba |  |  | 48" | 2026-04-25 |  | 50 | bare root | Walters Gardens |  | nice looking plants
HP2 | Kext | Astilbe chinensis | Vision in Pink |  |  |  | 2019-10-24 |  | 1-50 |  | North Creek
HP2 | Lext | Anemone x hybrida | Honorine Jobert |  |  |  | 2019-10-24 |  | 2-21 |  | North Creek
HP2 | Mext | Astilbe x arendsii | Bridal Veil |  |  |  | 2019-10-24 |  | 2-50 |  | North Creek
HP3 | A | Sedum | Autumn Joy |  |  | 48" | 2015-10-26 |  | 6 |  | Mom/division
HP3 | B | Sedum | Autumn Joy |  |  | 48" | 2017-08-25 |  | 32 |  | transplant/divide others
HP3 | C | Mountain Mint |  |  |  |  | 2019-06-26 |  | 6-72 |  | Roots cuttings |  |  | 10/16: these look awesome - a really good idea to rejuvenate/restart this way- bed has already completely filled in (process was to harvest old mountain mint & then rip out old bed/ restart with cuttings as soon as space was available for new planting)
HP3 | D | Veronicastrum virginicum |  |  |  |  | 2019-06-27 |  | 58 plants |  | North Creek
HP3 | E | Solidago | Little Lemon |  |  | 48" | 2018-05-10 |  | 1-32 | Ball
HP3 | F | Fritillaria | Ivory Bells |  |  | 48" | 2015-11-05 |  | 25 |  | Pete Roteveel
HP3 | G | Solidago | Little Lemon |  |  | 48" | 2016-08-30 |  | 100 (2-50's) |  | Swift Nurseries | Many astilbes in whole row look terrible; lost most in dry weather; planted around remaining few
HP3 | H | Solidago | Little Lemon |  |  | 48" | 2017-10-28 |  | 1-50 |  | Swift Nurseries
HP3 | I | Solidago | Little Lemon |  |  |  | 2019-06-10 |  | 1-50 |  | North Creek
HP3 | Jext | Solidago | rugosa Fireworks |  |  |  | 2019-10-15 |  | 4-50 |  | North Creek |  |  | 10/15/19: extend this bed to treeline
HP4 | A | Rhubarb |  |  |  | 48" | 2017-07-01 |  | 2 |  | Dad
HP4 | B | Achillea | Moonshine |  |  | 48" | 2020-07-31 |  | 2-72 |  | North Creek? |  | ones below did not perform as well 2020- rejuvenate with new plants
HP4 | B | Achillea | Moonshine |  |  | 48" | 2017-09-15 |  | 150 |  | Swift Nurseries |  | 10/8: filled in with some from HP6; lost a lot due to wet summer
HP4 | C | Lavender | Phenomenal |  |  | 48" | 2018-05-18 |  | 1-50 |  | Green Leaf (Ball) |  |  | replanted with all Phenomenal sometime in 2019
HP4 | D | Lavender | Phenomenal |  |  | 48" | 2016-05-17 |  | 48 | cuttings | Roots | fill in missing holes
HP4 | G | Peony | Sarah Bernhart |  |  | 48" | 2014-11-16 |  | 12 |  |  | 2/1 pattern
HP4 | H | Peony | Coral Charm |  |  | 48" | 2014-11-16 |  | 20 |  |  | 2/1 pattern
HP4 | I | Peony | Charles White |  |  | 48" | 2014-11-16 |  | 64 |  |  | probably some coral charm mixed in; 2/1 pattern
HP4 | Jext | Chrysanthemum | Matchsticks |  |  |  | 2020-11-03 |  | 32 |  | GET Group (Ball)
HP4 | Kext | Dendranthema | Clara Curtis |  |  |  | 2020-11-03 |  | 32 |  | GET Group (Ball)
HP4 | Lext | Helleborus | Apricot Blush |  |  |  | 2021-11-03 |  | 64 |  | GET Group (Ball)
HP4 | Jext |  | lysmiachia clethroides
HP5 | A | Sedum | Autumn Joy |  |  | 48" | 2015-10-26 |  | 5 |  | Mom/division
HP5 | B | Sedum | Autumn Joy |  |  | 48" | 2014-12-15 |  | 12 |  |  | 2/1 pattern
HP5 | B | Baptisia | Plum Rosy |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens
HP5 | C | Baptisia | Twilight Prarie Blues |  |  | 48" | 2014-11-20 |  | 42 |  |  | 1/1 pattern
HP5 | D | Baptisia australis |  |  |  | 48" | 2014-11-20 |  | 20 |  |  | 1/1 pattern
HP5 | E | Baptisia | australis |  |  |  | 2018-10-10 |  | 22 |  | GreenLeaf Nurseries
HP5 | F | Baptisia | Twilight Prarie Blues |  |  |  | 2020-06-02 |  | 3-21 |  | North Creek
HP5 | F | Baptisia | Purple Smoke |  |  |  | 2019-10-15 |  | 2-50 |  | North Creek |  | did not overwinter
HP5 | F.2 | Peony | Duchesse de Nemours |  |  | 48" | 2014-11-16 |  | 6 |  |  | 2/1 pattern
HP5 | G | Peony | Jules Elie |  |  | 48" | 2014-11-16 |  | 24 |  |  | 2/1 pattern
HP5 | H | Peony | Felix Crousse |  |  | 48" | 2014-11-16 |  | 11 |  |  | 2/1 pattern
HP5 | I | Peony | Krinkled White |  |  | 48" | 2014-11-16 |  | 8 |  |  | 2/1 pattern
HP5 | J | Peony | ASSORTED |  |  | 48" | 2014-11-16 |  | 22 |  | Susie Bear | 2/1 pattern
HP5 | K | Peony | Red | Cheryl Pauli |  | 48" | 2015-06-22 |  | 15 |  | Cheryl Pauli | 2/1 pattern
HP5 | L | Peony | Red | Cheryl Pauli |  | 48" | 2015-06-22 |  | 11 |  | Cheryl Pauli | 2/1 pattern
HP4 | Mext | Boxwood | Green Mountain |  |  |  | 2019-10-30 |  | 26 |  | Spring Meadow | 3 rows
HP6 | A | Asparagus |  |  | 5' | 48" | 2016-04-18 |  | 20 |  | Dad | 3 rows planted tight
HP6 | B | Sedum | Autumn Joy |  |  |  | 2016-09-09 |  | 2-72 |  | Greenleaf Nurseries
HP6 | B | Sedum | Autumn Joy |  |  |  | 2017-04-10 |  | 10 plants |  | fill in dead gaps
HP6 | D | Achillea | Moonshine |  |  |  | 2018-10-10 |  | 3-21 |  | Greenleaf Nurseries
HP6 | E | Rudbeckia | Henry Eilers |  |  |  | 2016-09-06 |  | 2-32's |  | North Creek Nusery
HP6 | F | Rudbeckia | Henry Eilers |  | 10' | 48" | 2015-06-30 |  | 50 |  | North Creek Nusery | 3/4 pattern
HP6 | G | Peony | ASSORTED |  |  | 48" | 2014-11-16 |  | 19 |  |  | 2/1 pattern
HP6 | Hext | Boxwood | Green Mountain |  |  |  | 2019-10-30 |  | 26 |  | Spring Meadow | 2 rows
HP7 | B | Tansy vulgare |  |  |  |  | 2017-05-17 |  | 1 1/2-72 | Roots |  | to fill in where Joe Pye died
HP7 | C | Eupatorium | Baby Joe |  |  |  | 2016-04-29 |  | 13 | bareroot | ASCFG TRIAL | 1/1 pattern |  | very large bare root plants
HP7 | C | Eupatorium | Baby Joe |  |  |  | 2016-09-09 |  | 28plants |  | Greenleaf Nurseries
HP7 | C | Peony | White | Cheryl Pauli |  |  | 2015-06-23 |  | 46 |  | Cheryl Pauli
HP7 | D | Peony | White | Cheryl Pauli |  |  | 2015-06-22 |  | 35 |  | Cheryl Pauli
HP7 |  | Kniphophia | Flashpoint |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens
HP7 |  | Kniphophia | Lucky Lemons |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens
HP7 | E | Physostegia | Pink Manners |  |  |  | 2016-04-29 |  | 14 | ellepot | ASCFG TRIAL | 2/3 pattern
HP7 | F | Stokesia | Mels Blue |  |  |  | 2016-04-29 |  | 14 | ellepot | ASCFG TRIAL | 2/3 pattern
this row ends at HP8 where triangle starts
HP8 triangle | A | Panicum | Apache Rose |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | B | Achillea | Sassy Summer Sangria |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Achillea | Sassy Summer Lemon |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Achillea | Peter Cottontail |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Achillea | Firefly Diamond |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | C | Pennisetum | Puppy Love |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | D | Muhlenbergia reverchaii |  | Undaunted |  |  | 2019-10-15 |  | 1-50 |  | North Creek
HP8 triangle | E | Baptisia | Pink Lemonade |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | F | Phlox | Fashionably Early Flamingo |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | G | Baptisia | Lemon Meringue |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Phlox | Glamour Girl |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Phlox | Opalexcence |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Phlox | Fasionably Early Crystal |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle |  | Penstemon | Onyx & Pearls |  |  |  | 2020-05-19 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | H | Vernoica | Blue Skywalker |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | I | Vernoica | Lavender Lightsaber |  |  |  | 2019-06-10 |  | 12 |  | Walters Gardens ASCFG TRIAL
HP8 triangle | j | Lavender | Phenomenal |  |  |  | 2019-06-10 |  | 1-50 |  | North Creek
this row ends at 8.2ext
HP8.2 | A.a | Baptisia australis |  |  |  |  | 2016-09-09 |  | 2-50 |  | North Creek | REPLANT- lost many in dry summer
HP8.2 | B-C | Baptisia australis |  | around living eryngium/ lost most | [7 empty] | REPLANT- lost many in dry summer
HP8.2 | B | Baptisia australis |  |  |  |  | 2018-10-10 |  | 50 |  | Green Leaf Nurseries
HP8.2 | D | Pennisetum alopecuroides viridescens |  |  |  |  | 2016-06-02 |  | 1-72 |  | Roots
HP8.2 | E | Baptisia australis | [9 empty] | REPLANT- lost many in dry summer
HP8.2 | F | Quaking Oat Grass |  |  |  |  | 2016-05-03 |  | 5 |  | Rachel | in triangle bed where lanterns meet P8.2
HP8.2 | E | Chasmanthium latifolium |  |  |  |  | 2019-10-30 |  | 1-50 |  | North Creek |  | also wraps down to HP7
HP8.2ext | F | Deutzia gracilis |  | Nikko |  |  | 2019-10-25 |  | 18 |  | Spring Meadow
HP9 | B | Viburnum opulus 'Roseum' |  |  |  |  | 2015-05-11 |  | 16 |  | Springmeadow | Andrew Hoover ordered these for me |  |  |  | 5/16/19: pruned all these: one row high up in plants, one row at 18"; not sure what is best
HP9 | B.2 | Viburnum opulus 'Roseum' |  |  |  |  | 2016-05-02 |  | 2 |  | Springmeadow | fill in dead ones
HP9 | C | Dogwood 'Artic Fire' |  |  |  |  | 2015-05-11 |  | 18 |  | Springmeadow | 2/1 pattern | ALL shrub rows on 10' spacing (center of row to next center of row)
HP9ext | D | Dogwood 'Artic Fire' |  |  |  |  | 2019-10-30 |  | 36 |  | Springmeadow | 3Rows-then lowest ow is Deutzia listed in 8.2ext |  |  | 3rows
HP10 | A | Viburnum opulus 'Roseum' |  |  |  |  | 2016-05-02 |  | 3 |  | Springmeadow
HP10 | B | Tree Peony |  |  |  |  | 2015-05-07 |  | 3 |  | move
HP10 | C | Viburnum 'Blue Muffin' |  |  |  |  | 2015-05-07 |  | 2 |  | Lurgan
HP10 | D | Viburnum nudum | Winterthur' |  |  |  | 2015-05-07 |  | 2 |  | Lurgan
HP10 | E | Viburnum carlesii |  |  |  |  | 2015-05-07 |  | 2 |  | Lurgan
HP10 | F | Hydrangea | Quickfire |  |  |  | 2015-05-07 |  | 1 |  | move
HP10 | G | Syringa | Tom Zuzgo |  |  |  | 2015-04-07 |  | 1 |  | move
HP10 | H | Viburnum opulus 'Roseum' |  |  |  |  | 2015-04-07 |  | 11 |  | move | 6' in row spacing
HP10 | I | Euyonomus 'Manhattan' |  |  |  |  | 2015-04-07 |  | 10 |  | move | double row |  | replaqnt 10/15/19 20 plants
HP10 | I.1 | Euyonomus 'Manhattan' |  |  |  |  | 2016-05-02 |  | 3 |  | cuttings; roots | fill in dead ones
HP10 | J | Euyonomus 'Manhattan' |  |  |  |  | 2019-10-25
HP10 | K | Physocarpus 'Diablo' |  |  |  |  | 2015-04-07 | 9/5/15 (3) | 4 |  | move | 1 remaining
HP10ext | L | Euyonomus 'Manhattan' |  |  |  |  | 2019-10-25 |  | 56 |  | cuttings; roots
HP11 | A | Hydrangea paniculata 'Limelight' |  |  |  |  | 2015-08-24 |  | 18 |  | Springmeadow | Andrew Hoover ordered these for me
HP11 | B | Hydrangea paniculata 'Limelight' |  |  |  |  | 2016-05-02 |  | 12 |  | Springmeadow
HP11 | C | Viburnum opulus 'Roseum' |  |  |  |  | 2016-05-02 |  | 7 |  | Springmeadow
HP11 | D | Juniperus | ? |  |  |  | 2015-11-02 |  | 2 |  | Diller
HP11 | E | Weigela |  |  |  |  | 2018-10-15 |  | 2 |  | fill in where 2 Arizonas died
HP11 | E | Cupressus | Arizona |  |  |  | 2015-09-15 |  | 3 |  | Lurgan
HP11ext | F | Hydrangea paniculata 'Limelight' |  |  |  |  | 2019-10-30 |  | 11 |  | Springmeadow
HP12 | all | Hydrangea paniculata 'Limelight' | [6 empty] | 41 |  | trans from old farm | 4' in row spacing
HP12ext | B | Hydrangea paniculata 'Limelight' |  |  |  |  | 2019-10-30 |  | 12 |  | Springmeadow
HP13 | AA | Giant Pussywillow |  |  |  |  | 2017-11-05 |  | 6 |  | Roots cuttings
HP13 | A | Hydrangea | Zinfindoll |  |  |  | 2016-08-30 |  | 15 |  | Springmeadow
HP13 | B | Viburnum | Winterthur' |  |  |  | 2016-08-30 |  | 15 |  | Springmeadow
HP13 | B | Viburnum | Brandywine |  |  |  | 2019-10-30 |  | 5 |  | Springmeadow
HP13 | C | Blueberry | Patriot |  |  |  | 2016-05-26 |  | 3 |  | Boyer Nursery
HP13 | D | Blueberry | BlueRay |  |  |  | 2016-05-26 |  | 2 |  | Boyer Nursery
HP13 | E | Blueberry | Berkley |  |  |  | 2016-05-26 |  | 3 |  | Boyer Nursery
HP13 | F | Chanomeles | Double Take | Orange |  |  | 2016-05-24 |  | 15 |  | Springmeadow | on 6' weedbarrier
HP13 |  | Chamaecyparis | Gold Mops |  |  |  | 2018-10-15 |  | 5 | fill in holes in whole row
HP14 | A | Giant Pussywillow |  |  |  |  | 2016-06-02 |  | 18 | cuttings | Roots
HP14 | B | Curly Willow -RED |  |  |  |  | 2016-06-02 |  | 67 | cuttings | Roots

## Big Field
Field/Row (from south to north, start at fence) | Order (from West to East, start at greenhouse) | Crop | Variety | Color | Length (feet) | Actual Date In | Date Out | Number of plants | How started | Source | Pattern | Notes
ODD=staked |  |  | TRIAL |  | full row |  | PLAN 2020
PLAN 2020:
Gomphrena: upper 1-7, 2300 plants per row
Asters: WFF2,4,6,8 BF2, 4 (1/2)
Marigold: WFF1 BF 1,3,5
BF1 | A | Marigold | Chedi | Orange |  | 2020-04-29 |  | 2.3-128 |  | Norman | 2/1 spacing | these took a frost in early May- came through better than WFF1 |  | Cockscomb: WFF 3,5,7 BF 7,9,11 (goal 2700 plants/BF row; 1700 plants/WFF row = 6/linear foot)
BF1 | B | Marigold | Coco | Gold |  | 2020-05-13 |  | 1-128 |  | Norman | 2/1 spacing | extras |  | Basil: BFWB
BF1 | C | Marigold | Coco | Deep Orange |  | 2020-05-13 |  | 1-128 |  | Norman | 2/1 | extras |  | Plume (trans): BF 6, 8, 10
BF1 | D | Marigold | Unknown |  |  | 2020-05-13 |  | 1-128 |  | Norman | 2/1 | extras |  | Plume (DS): BF 10,12 for 6/1,6/20. EFF 7/1, 7/20, 8/1
BF1 | E | Marigold | Mayan | Orange |  | 2020-05-18 |  | 1-72 |  | Roots | 2/1 |  |  | Ageratum: BF12
BF1 | F | Marigold | Coco | Deep Orange |  | 2020-05-18 |  | 7-72 |  | Roots | 2/1 |  |  | Salvia leucantha: WFF 10?
BF1 | G | Marigold | Jedi | Orange |  | 2020-05-18 |  | 8-72 |  | Roots | 2/1 |  |  | Blue Salvia: BF13 far end
BF1 | H | Marigold | Jedi | Orange |  | 2020-06-01 |  | 1.5-72 |  | Roots | 2/1 |  |  | Eucalyptus: WFF 9
Lisy: BF13
BF2 | A | Aster | Matsumoto | White |  | 2020-07-01 |  | 3-128 |  | Roots |  |  |  | Suns: Upper 8-24 (start at 24), then move to EU
BF2 | B | Aster | Matsumoto | Light Blue |  | 2020-07-01 |  | 5-128 |  | Roots |  |  |  | Sorghum/Millet/Amaranth: UpperRear 8-16
BF2 | C | Aster | Matsumoto | Light Blue |  | 2020-07-14 |  | 23-128 | or 72? | Roots |  |  |  | Rudbeckia/Matricaria/Helichrysum?: EFF
BF2 | D | Aster | Matsumoto | Blue |  | 2020-07-14 |  | 23-128 | or 72? | Roots |  |  |  | Snaps/maybe spring Brassicas: EFF spot where willow removed
BF2 | E | Aster | Matsumoto | Blue |  | 2020-07-30 |  | 4-128 | [5 empty] | Dianthus: BF Rear
Brassicas (outdoor)/Late Ammi/Daucus: BF Rear
BF3 | A | Marigold | Chedi | Yellow |  | 2020-05-18 |  | 1-72 |  | Roots |  |  |  | Stake ODD Rows WFF/BF
BF3 | B | Marigold | Saved Crazy Orange |  |  | 2020-06-23 |  | 1-72 |  | Roots |  |  |  | Rotation:
BF3 | C | Marigold | Royal Ball Gold |  |  | 2020-06-23 |  | 1-72 |  | Roots |  |  |  | WFF out 9/1; lay plastic in fall for cool annuals- by 9/15. | things that go in after 7/1: 900' asters, 250' marigolds, 300' DS plume (7/20, 8/2)
BF3 | D | Marigold | Nosento | Lime Green |  | 2020-06-23 |  | 1-72 |  | Roots | 2/1 |  |  | 2021: cool annuals WFF; out 7/1; maybe lay plastic for late annuals?
BF3 | E | Marigold | Hermant | Deep Gold |  | 2020-06-23 |  | 1-72 |  | Roots | 2/1
BF3 | F | Marigold | Coco | Deep Orange |  | 2020-06-23 |  | 8-72 |  | Roots | 2/1 |  |  | BFRear: amazon neon, spring brassica. FALL outdoor brassicas |  | then: cabbage/kale/late ammi/daucus
BF3 | G | Marigold | Oriental | Gold |  | 2020-06-23 |  | 6-72 |  | Roots | 2/1
BF3 | H | Marigold | Xochi | Orange |  | 2020-07-08 |  | 1-72 |  | Roots | 2/1
BF3 | I | Marigold | Bangal | Orange |  | 2020-07-08 |  | 1-72 |  | Roots | 2/1
BF3 | J | Marigold | Janthra |  |  | 2020-07-08 |  | 1-72 |  | Roots | 2/1
BF3 | K | Aster | Matsumoto | White |  | 2020-07-30 |  | 2-128 |  | Roots | 2/1
BF3 | L | Aster | Matsumoto | Light Blue |  | 2020-07-30 |  | 8-128 |  | Roots | 2/1
BF3 | M | Aster | Matsumoto | Blue |  | 2020-07-30 |  | 4-128 |  | Roots | 2/1
BF4 | A | Celosia | SAVED | Mix Pinks |  | 2020-06-18 |  | DS-225' |  |  | excellent. Do same amount again
BF4 | B | Celosia | SAVED | Crested Pink |  | 2020-06-18 |  | DS-225'
BF5 | A | Aster | King Sized | Apricot |  | 2020-07-01 |  | 2-128 |  | Roots | 3/2 space
BF5 | B | Marigold | Oriental | Deep Gold |  | 2020-07-08 |  | 10-72 |  | Roots | 3/2 space
BF5 | C | Marigold | Jedi | Orange |  | 2020-07-08 |  | 10-72 |  | Roots | 2/1
BF5 | D | Celosia | Forest Fire |  |  | 2020-07-08 |  | 7-72 |  | Roots | 2/1
BF5 | E | Celosia | DS Saved Yellow |  |  | 2020-07-08 |  | DS |  |  | 3/2
BF6 | A | Celosia | Sunday | Cherry |  | 2020-05-18 |  | 6-128 |  | Norman | 3/2 tight
BF6 | B | Celosia | Sunday | Orange |  | 2020-05-18 |  | 6-128 |  | Norman | 3/2 tight
BF6 | C | Celosia | Sunday | Bright Pink |  | 2020-05-18 |  | 6-128 |  | Norman | 3/2 tight
BF6 | D | Celosia | Sunday | Pink SAVED |  | 2020-05-27 |  | 10-72 |  | Roots | 3/2 tight | 80% germ
BF6 | E | Celosia | Sunday | Orange SAVED-Darker stems |  | 2020-05-27 |  | .5-72 |  | Roots | 3/2 tight
BF6 | F | Celosia | Sunday | Orange SAVED |  | 2020-05-27 |  | 1-128 |  | Norman | 3/2 tight | extras
BF7 | A | Celosia | Chief | Fire |  | 2020-06-03 |  | 36-72 |  | Roots
BF7 | B | Celosia | Chief | Persimmon |  | 2020-06-03 |  | 12.5-72 |  | Roots
BF8 | A | Celosia | SAVED | Magenta |  | 2020-05-27 |  | 6-72 |  | Roots | 3/2 space
BF8 | B | Celosia | SAVED | Yellow |  | 2020-05-27 |  | 12-72 |  | Roots | 3/2 space
BF8 | C | Celosia | Forest Fire |  |  | 2020-05-27 |  | 2-72 |  | Roots
BF8 | D | Celosia | SAVED | Pink |  | 2020-06-09 |  | DS | 200' |  | 3/2 tight
BF8 | E | Celosia | Sunday Orange |  |  | 2020-06-09 |  | DS | 100' |  | 3/2 tight
BF8 | F | Celosia | Sunday | Orange -SAVED |  | 2020-05-27 |  | 8-72 |  | Roots | 3/2 tight | TERRIBLE GERM
BF9 | A | Celosia | Chief | Persimmon |  | 2020-06-03 |  | 25.5-72 |  | Roots
BF9 | B | Celosia | Kurume | Orange Red |  | 2020-06-16 |  | 20-72 |  | Rooots | 3/2 tight | 90% germ
3/2 space
BF10 | A | Celosia | SAVED | Orange |  | 2020-06-10 |  | 6-72 |  | Roots | 3/2 space
BF10 | B | Celosia | SAVED | Magenta |  | 2020-06-10 |  | 24-72 |  | Roots
BF10 | C | Celosia | Act Rima | Rose |  | 2020-06-10 |  | 2-72 |  | Roots
BF10 | D | Celosia | Cristi | Purple |  | 2020-06-10 |  | 2-72 |  | Roots | 3/2 space | very hot this day; lost some to transplant shock
BF10 | E | Celosia | Red Ace |  |  | 2020-06-10 |  | 2-72 |  | Roots | 3/2 space
BF10 | F | Celosia | SAVED | Peach |  | 2020-06-10 |  | 6-72 |  | Roots | 3/2 space
BF10 | G | Celosia | SAVED | Sunday Orange |  | 2020-06-09 |  | DS |  | 40' | 3/2 space
3/2 space
BF11 | A | Celosia | Chief | Fire |  | 2020-06-10 |  | 40-72 |  | Roots | 3/2 space
BF11 | B
BF12 | A | Ageratum | Blue Sensation | Saved |  | 2020-05-13 |  | 7.75-48 |  | Janet |  | saved seed- poor germ
BF12 | B | Ageratum | Blue Horizon |  |  | 2020-05-27 |  | .25-128 |  | Norman |  | leftovers
BF12 | C | Ageratum | Blue Sensation | SAVED |  | 2020-06-23 |  | 11-72 |  | Roots
BF12 | D | Salvia | leucantha |  |  | 2020-07-17 |  | 4-72 |  | Roots cuttings |  | 2/1 space wide
BF12 | C | Salvia | leucantha |  |  | 2020-06-23 |  | 6.5-72 |  | Roots cuttings
BF12 | E | Salvia | leucantha |  |  | 2020-06-10 |  | 2-18 |  | Lurgan
BF12 | F | Salvia | leucantha |  |  | 2020-06-10 |  | 3-72 |  | Roots cuttings
BF13 | A | Lisianthus | Advantage Purple |  |  | 2020-05-13 |  | 12-72 |  | Norman |  | 5/4 space | potted up from 288 in April
BF13 | B | Lisianthus | Arena | Red |  | 2020-05-13 |  | 7-72 |  | Norman |  | 5/4 space | potted up from 288 in April
BF13 | C | Lisianthus | Rosita | Saphire |  | 2020-05-13 |  | 4-72 |  | Norman |  | 5/4 space | potted up from 288 in April
BF13 | D | Celosia | Saved Cramers Burgundy |  | DS | [6 empty] | can't remember when seeded- maybe 7/1- but did REALLY WELL!
BF13 | E | Salvia | Blue Bedder |  |  | 2020-05-27 |  | .6-128 |  | Norman |  | leftovers
BF13 | F | Salvia | Victoria Blue |  |  | 2020-05-27 |  | 5-48 |  | Norman |  | leftovers
BF13 | G | Salvia | Victoria Blue |  |  | 2020-04-27 |  | 11-48 |  | Janet
BF13 | H | Salvia | Blue Bedder |  |  | 2020-04-27 |  | 16-48 |  | Janet
BF14 | A | Eucalpytus | Silver Drop |  |  | 2020-05-13 |  | 1-128 |  | Norman | 3/2 space med
BF14 | B | Eucalpytus | Lemon |  |  | 2020-05-13 |  | 2-48 |  | Janet | 3/2 space med
BF14 | C | Peppers | Candles On Top | Orange |  | 2020-05-21 |  | 1-128 |  | Norman
BF14 | D | Peppers | Candles On Top | Red |  | 2020-05-21 |  | 1-128 |  | Norman
BF14 | E | Peppers | Bell, asst |  |  | 2020-05-27 |  | 24
BF14 | F | Celosia | Forest Fire |  |  | 2020-07-08 |  | 13-72 |  | Roots
BF14 | G | Celosia | SAVED ORANGE |  |  | 2020-07-08 |  | 4-72 |  | Roots
BF14 | H | Rudbeckia | Sahara |  |  | 2020-07-08 |  | 2-72 |  | Roots
BF14 | I | Scabiosa | Cut Brite |  |  | 2020-05-27 |  | 4-72 |  | Roots
BF14 | J | Scabiosa | stellata |  |  | 2020-05-13 |  | 4-72 |  | Roots
BF14 | K | Strawflower | Fireball |  |  | 2020-05-13 |  | 8 plants |  | Janet
BF14 | L | Strawflower | King Size | Mix |  | 2020-05-13 |  | 3.25-48 |  | Janet | 4/3 | poor germ
BF14 | M | Strawflower | King Size | Mix |  | 2020-05-13 |  | 2.75-72 |  | Roots
BF14 | N | Clarkia | Elegant Salmon |  |  | 2020-05-13 |  | 6-48 |  | Janet
BF15 Weed Barrier | A | Basil | Sweet Dani |  |  | 2020-05-14 |  | 19-48 |  | Janet
BF15 Weed Barrier | B | Basil | Sweet Dani |  |  | 2020-06-02 |  | 6-72 |  | Roots
BF16 Weedbarrier | A | Celosia | Saved Magenta |  |  | 2020-06-09 |  | DS | 140'
BF16 Weedbarrier | B | Basil | Sweet Dani |  |  | 2020-06-02 |  | 18-72 |  | Roots
BF17 | A | Celosia | SAVED Magenta |  |  | 2020-07-07 | 100' | DS open ground |  | these did OK, but were not irrigated so were very slow. Need to run drip if it's a dry summer. Could have used 600'
BF17 | B | Celosia | SAVED Yellow |  |  | 2020-07-07 | 130' | DS open ground
BF18 | A | Celosia | SAVED peach |  |  | 2020-07-21 | 200' | DS open ground
BF19 | A | Celosia | SAVED burgundy cockcscomb |  |  | 2020-07-21 | 200' | DS open ground
BF20 Weed Barrier | A | NO BF20 this year.
BFRear15 | A | Ammi visnaga |  |  |  | 2020-07-07 |  | 60'
BFRear15 | B | Artemesia | Sweet Annie |  |  | 2020-05-12 |  | 10' hand seed
BFRear16 |  | Orlaya |  |  |  | 2020-07-07 |  | 85'
BF18Rear | all | Dianthus | Bouquet | Purple |  | 2019-08-30 |  | 18.5-72 |  | Roots
BF20Rear | all | Dianthus | Bouquet | Purple |  | 2019-08-30
BF21Rear | A | Dianthus | Bouquet | Purple |  | 2019-08-30
BF21Rear | B | Dianthus | Electron | Mix |  | 2019-08-30 |  | 20-72 |  | Roots | was actually 20T; poor germ
BF22Rear | all | Dianthus | Electron | Mix |  | 2019-08-30
BF23Rear | all | Dianthus | Electron | Mix |  | 2019-08-30

## Task Calendar
| completed |  | office | fertility | field work | planting | spray
Goals 2020:
January |  |  | orders: | Janet Hoover | [5 empty] | Crew | all done by noon on Fridays
|  |  |  | Geo Seed; Gloeckner; Johnnys; Renees | [6 empty] | schedule time off in October for EM, KZ, ME for rejuvenation before wreath season
|  |  |  | Mums | [6 empty] | incentivize to finish by 4:30 on bouq days: chart, lunch treat, etc.
|  |  |  | Dahlias | [6 empty] | Michelle in office on Friday mornings
| 2020-01-25 |  |  | Norman/Sunrise | [6 empty] | language around "what does finished task look like?"
| 2020-01-25 |  | budget | [7 empty] | Kenze to be crew leader; strengthen her leadership & my communication to her
|  |  | staff plan | [7 empty] | weekly meeting Monday 7am
|  |  | Facebook & insta campaigns | [6 empty] | Projects | wagon shed doors; paint all
| 2020-01-30 | 15-20 | bring in tulip crates | [7 empty] | cement pad outside lower barn entrance
|  | 15 | start ranunculus corns | [7 empty] | new sunflower seeding system
break ground East Upper- have a plan for 2021 rotation
water hardness/acid injector/learn system
WELL????
System Improvements
February |  |  | HIRE/STAFF plan | [7 empty] | sunflower seeding
|  |  | make twig wreaths | [7 empty] | prop house space utilization
| did all at once |  | bring in rest of tulip crates | [7 empty] | prop house water
prop house sanitation
communication chain
March | 2020-01-30 |  | check on all perennials; update crop plan/map | [6 empty] | Equipment
|  |  | finalize all Wegs/Karns plan; visit stores; print labels BE DONE BY 3/30 | [7 empty] | get rid of unused things: golf cart? Metal seed starting carts? Unused display pieces?
new wreath boards
April |  |  | monitor moisture levels for larkspur, dianthus, etc | [7 empty] | new wreath table with hammerless clamp machine?
|  |  | stake yarrow! Stake low, but must be staked. Lost so much two years in a row | [7 empty] | consider sleeving cart/station instead of big table
| 2020-04-12 |  | do personality tests with whole crew | [6 empty] | Sales outlets
|  |  | till new East Upper Field- seed buckwheat | [7 empty] | more DIY buckets, drieds, etc.
|  |  | tarp Upper Rear for sorghum | [7 empty] | surprise pop-ups for abundance
grow Wegs, of course
May | 2020-06-01 |  | order ranunculs ** how much? Whole bed=1000 corms | [7 empty] | corporate accounts: 2-3 Christmas orders and 2-3 new institutional clients for fresh
|  | WFF:5/25 | fertilize BF | [5 empty] | did 1/3 bag 12-28-8 on WFF3, WFF 5, WFF 7, WFF9
|  | 25 | calcium on lisy, especially if dark & rainy
spray every single sunflower planting for downy in all of May/early June. They are suffering now (6/26)
| 2020-06-02 |  | pinch Sunday plume celosia in field for longer side shoots
| 2020-05-15 |  | harvest snowball viburnum GREEN for longer vaselife & less petal drop. These change from green to white in about 3 days- don’t' miss harvest window.
| constant |  | take mum & salvia leucantha cuttings
June |  |  | Take pictures of Michelle!
schedule karns sale week and sunflower week for July (ideal mid-July suns, week after for med bouq special)
| 2020-06-16 |  | review YE summary of bouqs/harvest/roles (in staff floder)
| 2020-06-10 |  | PREVENTATIVE SPRAY for disease first week of June. Huge disease pressure now (6/26). Spray pretty much whole field for various diseases (early blight gomph, spots on celosia, downy on suns, downy on basil)
spray suns at every emergence. Especially early on. They are set back due to downy, even when we grow resistant varieties
| 2020-06-08 | 10 | fertilize BF
|  | 25 | fertilize BF
| no crabgrass, so dry |  | schedule time to hoe/weed edges of plastic in mid/late June before weeds get so big & out of hand; a quick hoe can scratch out crabgrass seedlings | [8 empty] | plastic: no record of when Lloyd came. Or anything. Laid 2biotelo & 2 biogold. I think biogold first, but unsure. Way less holes in irrigation this season, but gomphrena in upper did have many holes.
harvest dill and ammi very deep into plants for longer side shoots
|  |  | take mum cuttings | [8 empty] | needed for fall/popup: 100 grapevine wreaths, white gomph, white & red strawflowers, sweet gum balls, acorns, all sizes pinecones- who's going to the beach???
|  |  | take salvia leucantha cuttings | [8 empty] | NEW GREENS source!! Douglas? Fraser??
|  | 20 | set up sprinkler on 6/20 ds crops for better germ
| 2020-07-01 |  | spray japanese beetles at first observance; continue when bad so pheremones don't draw more
make sure to dry enough wheat & larkspur - comes on fast, but really useful in fall- esp blue & purple
July |  |  | Take pictures of Michelle!
schedule karns sale week and sunflower week for August (ideal mid-Aug suns, week after for med bouq special)
pay attention to 6/20 and 7/10 ds crops for weeds and proper soil moisture for germ
set up sprinkler on 7/10 ds crops for better germ
spray zinnias for powdery mildew (cease)
August |  |  | Take pictures of Michelle!
pay attention to 6/20 and 7/10 ds crops for weeds and proper soil moisture for germ
pinch amaranthus after it's up
scout ghse for thrips
spray zinnias for powdery mildew (cease)
spray lisy for thrips (gh & field)
monitor hydrangea for japanese beetles
monitor hairy balls for aphids
September |  |  | Take pictures of Michelle!
preventative spray celosia for spots
spray zinnias for powdery mildew (2x)
scout ghse for thrips
spray cabbages for aphids & worms (bt and something for aphids)
spray lisy for thrips (gh & field)
watch mums for rust
turn Mike's dirt piles on hill so pennycress germinates
October |  |  | order lilies | [5 empty] | 6/2: delete pink lily planting early. Otherwise so far so good. Is there a stronger soft orange? Mynnou seems to wash out in the vase. GHSE is stuffed with lilies. MUST COME up with another plan for them if we grow this many again.
work out all details of wreath season: sources, marketing, staffing (keep it lean!), Michelle time off
order seeds for 20% discount!!!!
Martin's greenhouse supply early buy
plant tulips
plant anemones/ranunculus/snapdragons
scout ghse for thrips
spray lilies with cease for botrytis
spray cabbages for aphids & worms
November |  |  | stay true to myself and Roots!
December |  |  | start Norman Martin order- Due January 10
Martins early buy
ORDER POPPIES- they sell out
dry more: |  |  | craspaedia, sea holly, nigella, echinops, lavender |  |  |  |  | for bouts
|  |  | scabiosa, billy balls, white gomphrena |  |  |  |  | for boxwood trees
pictures of larger pieces, wedding ceremonies - especially on site; from professionals with wedding party
field pictures throughout season
records: sunflower differences; try to grow less kinds each planting? Is sunrich necessary?
Take pictures of Michelle!
greenhouse notes: layout: seedling bench 2T deep on north, then another 4T deep bench in middle. Overhead hose so can be tight spacing.
lilies to south ON DRIP; could be tight together with no walkway if maturity/harvest are far enough apart to get rid of one crop after harvest. Can slide whole lily crate row as needed (disconnect drip at trunk line, then reconnect)
5/26: lilies in center of three rows got very leggy; outer row bent outside of rollups. Need to figure out better plan
Plants to pursue: |  | caterpillar tunnel for spring planted ranunculus. Could have sold more in May if it hadn't pooped out
late blooming lilacs for Mothers Day
Bridal Veil spirea
Cherry Laurel
Myrtle in crates?
Nandina
Junipers, arizonas, leylands
perennials
white vernonica
solomons seal
lysimachia clethroides